Project name: Host-Pathogen Transcriptomic Transportability Project

Governing document: Use the uploaded document entitled Protocol for a Cross-Cohort Host-Pathogen Transcriptomics Project: Conserved and pathogen-ecology-specific whole-blood immune-metabolic programs across acute bacterial and viral infections as the governing protocol for this project.

Core mission: Conduct a rigorous, reproducible public-data transcriptomics study identifying conserved versus pathogen-ecology-specific whole-blood immune-metabolic programs across acute bacterial and viral infections, using pathway/module locking and independent external transportability testing.

Project boundaries: This project is separate from the TB-undernutrition transcriptomics study and all other manuscripts. It is not intended to develop another primary bacterial-versus-viral diagnostic classifier. Its primary scientific purpose is to understand conserved versus context-specific host-response biology.

Prespecified dataset roles:

- GSE211567: primary scientific discovery cohort and internal context-concordance analysis resource.

- GSE161731: primary adult external transportability cohort; it may be used earlier only for technical mastery of the count-level RNA-seq workflow without selecting biological modules.

- GSE261482: exploratory pediatric generalizability extension after the discovery-defined modules are frozen.

- GSE282464: conditional extension only after metadata, sample-composition and independence audits are resolved.

Mandatory analytical safeguards:

- Complete a formal metadata and file-availability audit before biological inference.

- Maintain a documented GitHub version-control and decision-log workflow.

- Do not select, reweight or reorient modules using external-cohort results.

- Freeze module definitions before interpreting adult or pediatric external testing.

- Apply an assay/feature-portability audit before external module scoring.

- Report negative, discordant or nontransportable findings honestly rather than modifying the study post hoc.

- Interpret whole-blood modules as systemic transcriptional programs unless additional analyses directly justify a more specific mechanism.